## Product Backlog
| User Stories |  |  | Acceptance criteria | Estimation Hours | Priority | Status | Function Name
| As a … | I want to ... | So That…
1 | As a user of a sneaker catalogue, | I want advanced search options on the front page | so that I can quickly and easily refine my search. | I can limit the search by brand / type | 96 | 1 | Completed | Searching + Sorting+Filter
I can limit the search by keywords
I can sort the releated result by statement
2 | As a internet surfers of the auction page, | I want to create user account on the page | so that I can auction before using the system. | I can make the own account for advanced use in follow information - User name - Password - Gender - Date of birth - Address - Phone - Email | 24 | 2 | Completed | Registration + Login
3 | As a user of the auction page, | I want to bid the shoes in auction website | so that I can auction before using the system. | I can select the related item for bid with the corresponding amount for my offer | 24 | 3 | Completed | Bid item
4 | As a user of the auction page, | I want to confirm the auction are processing with my offer | so that I can auction for the related items. | I can browse the bid record about my bid and sell | 6 | 4 | Completed | Browse bid record
I can know the date and price of my bid activities
5 | As a user of the auction page, | I want to post the shoes for selling in auction website | so that I can confirm the auction are processing with my offer. | I can set the product information for the item, the information include : - Product name - Post date - Days of post - Minimun price - Size of shoes - Brand - Color - Delivery method - Style code - Type of the shoes | 42 | 5 | Completed | Post Item
I can upload the product photos for the item
6 | As a user of the auction page, | I want to take a mark for my searched result | so that I can confirm the auction are processing for my products. | I can mark down the selected interest item | 12 | 6 | Completed | My Favourite
I can view my favourable items after next login
I can manage my favourable by increase / delete
7 | As a user of the auction page, | I want to get the latest bid for the items about my posted shoes | so that I can know the details related to my product. | I can get the notice about other's higher bid related my offer | 6 | 7 | Completed | Seller & Buyer Notification
I can get the notice about the bids related my product
8 | As a user of the auction page, | I want to simply modify my personal detail of my user account | so that I can change my account information. | I can modify of the address, phone number, and email for the user account | 6 | 8 | Completed | Personal Detail Modification
9 | As a user of the auction page, | I want the message board function on the page | so that I can quickly and easily leave a message or question for the related products. | I can enter the message under the evaluation of product | 12 | 9 | Completed | Comment Box
10 | As a user of the auction page, | I want the auction product ranking function on the front page | so that I can get information about the most interest items of all users. | I can view of the top 5 hot-sales items base on the purchase history | 12 | 10 | Completed | Ranking
|  |  | 6 members x 4 hours/week x 5 weeks (per Sprint) = 120 hours/sprint | Sprint 1 (Priority 1 - 2) | 120
|  |  | 6 members x 4 hours/week x 5 weeks (per Sprint) = 120 hours/sprint | Sprint 2 (Priority 3 - 10) | 120
|  |  | Grand Total | Sprint 1 + Sprint 2 | 240

## Sprint 1
ID | User Story | Task | Handler | Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14 | Day15 | Day16 | Day17 | Day18 | Day19 | Day20
1 | As a user of a sneaker catalogue, I want advanced search options on the front page so that I can quickly and easily refine my search. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 25 | 24 | 21 | 17 | 15 | 15 | 13 | 11 | 7 | 6 | 5 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | Yung Chun To, Samuel So Wai Lok | 4 | 3.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 60 | 60 | 53 | 45 | 38 | 37 | 32 | 30 | 25 | 21 | 15 | 8 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test the code | Whole Team | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As a internet surfers of the auction page, I want to create user account on the page so that I can auction before using the system. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test the code | Whole Team | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0
|  | Coding | Whole Team | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 14 | 14 | 14 | 8 | 4 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actualy | 120 | 117.75 | 106.75 | 91.75 | 82.75 | 81.75 | 74.75 | 70.75 | 61.75 | 54.5 | 47.5 | 35.5 | 23.5 | 26.5 | 24.5 | 10.5 | 5.5 | 1.5 | 0 | 0 | 0
|  |  | Ideal | 120 | 114 | 108 | 102 | 96 | 90 | 84 | 78 | 72 | 66 | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0

## Sprint 2
ID | User Story | Task | Handler | Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14 | Day15 | Day16 | Day17 | Day18 | Day19 | Day20
3 | As a user of the auction page, I want to bid the shoes in auction website so that I can auction before using the system. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 7 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 15 | 15 | 13 | 11 | 9 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As a user of the auction page, I want to confirm the auction are processing with my offer so that I can auction for the related items. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | As a user of the auction page, I want to post the shoes for selling in auction website so that I can confirm the auction are processing with my offer. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 30 | 30 | 28 | 26 | 24 | 23 | 21 | 19 | 17 | 15 | 13 | 11 | 9 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | As a user of the auction page, I want to take a mark for my searched result so that I can confirm the auction are processing for my products. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | As a user of the auction page, I want to get the latest bid for the items about my posted shoes so that I can know the details related to my product. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | As a user of the auction page, I want to simply modify my personal detail of my user account so that I can change my account information. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | As a user of the auction page, I want the message board function on the page so that I can quickly and easily leave a message or question for the related products. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | As a user of the auction page, I want the auction product ranking function on the front page so that I can get information about the most interest items of all users. | Design a user interface | Pun Cheuk Kwan Au Chi Chung Lam Kin Wa Fung Wai Yin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create and design a database table | So Wai Lok | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Coding | Whole Team | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | test the code | Whole Team | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Meeting with the team | Whole Team | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actualy | 120 | 118 | 107 | 94.5 | 82.5 | 73.5 | 65.5 | 59 | 47 | 36 | 24 | 15.5 | 11 | 9 | 7 | 5 | 0 | 0 | 0 | 0 | 0
|  |  | Ideal | 120 | 114 | 108 | 102 | 96 | 90 | 84 | 78 | 72 | 66 | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0