## Sprint Backlog #1
Sprint Backlog for Sprint No. 1
Priority | Story ID | Function | User Story/ Task | Person in charge | Status | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | 1 | Search Filter | As a user of a sneaker catalogue, I wanted an advanced search options in the front page so that I can refine my search quickly and easily.
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Au Chi Chung | Completed | 13 | 13 | 12 | 12 | 10 | 9.5 | 7 | 6 | 4.5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Yung Chun To Samuel | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | Register | As a internet surfer of the auction page, I want to create an user account so that I can enjoy member feature.
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Fung Wai Yin | Completed | 15 | 15 | 15 | 15 | 13 | 13 | 11 | 9 | 8 | 6.5 | 4 | 4 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Au Chi Chung | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 3 | Post Auction | As an auctioneer, I want to post the items in auction website so that I can sell my products
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Lam Kin Wa | Completed | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 12 | 10 | 10 | 8 | 8 | 6 | 6 | 4 | 4 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Fung Wai Yin | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
4 | 4 | Bid items | As a bidder, I want to bid the items in auction website so that I can buy products.
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 1.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | So Wai Lok | Completed | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13 | 12 | 11 | 10 | 8 | 8 | 6 | 6 | 4 | 4 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Lam Kin Wa | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
5 | 5 | Search Related Product | As an auctioneer, I want to confirm the website is processing with my offer so that I can compare similar product
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Pun Cheuk Kwan | Completed | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 12 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | So Wai Lok | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
6 | 6 | Confirm Auction Process | As an auctioneer, I want to confirm the website is processing my products so that I can ensure my auction
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Yung Chun To Samuel | Completed | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 12 | 11 | 10.5 | 8 | 8 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 2 | 2 | 1 | 0 | 0
|  |  | Testing and Debugging | Pun Cheuk Kwan | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  |  | Total Remaining Effort |  | 120 | 120 | 117 | 117 | 109.5 | 107.5 | 102 | 98 | 92.5 | 86.5 | 79 | 71 | 63.5 | 56.5 | 52 | 47 | 42.5 | 35.5 | 33 | 28 | 21 | 19.5 | 13 | 12 | 8.5 | 8.5 | 5 | 3 | 0
|  |  |  | Ideal line | 4.2857 | 120 | 115.71 | 111.42 | 107.13 | 102.84 | 98.55 | 94.26 | 89.97 | 85.68 | 81.39 | 77.1 | 72.81 | 68.52 | 64.23 | 59.94 | 55.65 | 51.36 | 47.07 | 42.78 | 38.49 | 34.2 | 29.91 | 25.62 | 21.33 | 17.04 | 12.75 | 8.46 | 4.17 | 0

## Sprint Backlog #2
Sprint Backlog for Sprint No. 2
Priority | Story ID | Function | User Story/ Task | Person in charge | Status | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
7 | 7 | Favourite List | As a bidder, I want to mark down for my searched result so that I can check again next time
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Au Chi Chung | Completed | 13 | 13 | 13 | 11 | 10 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Yung Chun To Samuel | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 8 | Modify Posted Product | As an auctioneer, I want to modify the details of my products so that I can update my product information.
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Fung Wai Yin | Completed | 12 | 12 | 12 | 12 | 12 | 11 | 9 | 7 | 6 | 4 | 4 | 3.5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Au Chi Chung | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 9 | Latest Information of products | As a bidder or auctioneer, I want to get the latest bid of the items about my bid/ post so that I have the latest news of the product.
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Lam Kin Wa | Completed | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 11 | 9 | 9 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Fung Wai Yin | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 10 | Related products base on past history | As a bidder or auctioneer, I want to view related products base on my bid/post so that I can buy similar product next time
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | So Wai Lok | Completed | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13 | 11 | 11 | 9 | 7.5 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Lam Kin Wa | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
11 | 11 | Message Board | As a bidder or auctioneer, I want to leave a message or question for the products so that I can contact with auctioneer/bidder.
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Pun Cheuk Kwan | Completed | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 11 | 9 | 7 | 5.5 | 3.5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | So Wai Lok | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1 | 0 | 0 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
12 | 12 | Product Ranking | As a bidder or auctioneer, I want to know about the most interested items of all users so that I can know the trend.
|  |  | Design User Interface | All group members | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coding | Yung Chun To Samuel | Completed | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 10 | 8.5 | 6 | 4 | 3.5 | 2 | 1 | 0 | 0 | 0 | 0
|  |  | Testing and Debugging | Pun Cheuk Kwan | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0
|  |  | Meeting with the team | All group members | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  |  |  | Total Remaining Effort |  | 120 | 120 | 118 | 116 | 113 | 109 | 105 | 101 | 97 | 94 | 91 | 88.5 | 85.5 | 79 | 70 | 66 | 60.5 | 49 | 41 | 32 | 25 | 19 | 15.5 | 11.5 | 9 | 5 | 3 | 1 | 0
|  |  |  | Ideal line | 4.2857 | 120 | 115.71 | 111.42 | 107.13 | 102.84 | 98.55 | 94.26 | 89.97 | 85.68 | 81.39 | 77.1 | 72.81 | 68.52 | 64.23 | 59.94 | 55.65 | 51.36 | 47.07 | 42.78 | 38.49 | 34.2 | 29.91 | 25.62 | 21.33 | 17.04 | 12.75 | 8.46 | 4.17 | 0